## Risk Based Calculation
Relative Weights (1-low, 5-high)
Owner | PM |  | Dev |  |  | Test | [6 empty] | TTL MH | Risk% | Coverge% | OPT MH | AVG SUF%
Weight | 1 |  | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 56 | 13.53% | 86.47% | 40 | 100%
FRID | Impact | Usage | Impact | Usage | D-PoF | Impact | Usage | T-PoF | EXECost (MH) | Total Impact | Total Usage | Total PoF | EXECost Scale | Risk Values | Priority | Covered (n)? | Test SUF% | Prerequisites
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | y | 100%
2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 8 | 2.6667 | n | 100% | 1
3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | 18 | 4.5 | y | 100% | a
4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 4 | 4 | 4 | 3 | 32 | 5.3333 | y | 100% | 1,2
5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 5 | 5 | 5 | 3 | 50 | 6.25 | y | 100%
6 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 5 | 13 | 2 | 2 | 4.5 | 5 | 18 | 1.3846 | n | 100%
7 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 10 | 3 | 3 | 1.5 | 4 | 9 | 0.9 | y | 100%
8 | 5 | 1 | 5 | 1 | 3 | 5 | 1 | 3 | 5 | 5 | 1 | 3 | 3 | 18 | 3.6 | y | 100%
9 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1.6667 | 2.6667 | 4 | 2 | 17.3333 | 4.3333 | y | 100%
10 | 4 | 3 | 2 | 1 | 5 | 4 | 3 | 2 | 1 | 3.3333 | 2.3333 | 3.5 | 1 | 19.8333 | 19.8333 | y | 100% | 1,2,3,4,5,6

## Instructions
Risk Based Coverage process instructions
Worksheet Input Columns:
Weight - the relative weight for each stakeholder in the decision-making process
FRID - the unique Functional Requirement Identifier for a functional requirement in the Test Plans' "Functional Requirements " table.
Impact - defines the operational impact on customer (i.e. primary user scenarios) if this functional behavior does not work.
Usage - defines how often a behavior is triggered.
D-PoF - defines the "Dev Probability of Failure" measurement (expectation) of a failure (from known structural complexity or issues)
T-PoF - defines "Test Probability of Failure" measurement (expectation) of a failure ( e.g. area is known to be problematic from our previous test experience)
EXECost MH - the estimated Execution Cost in Man Hours to verify a functional requirement
Covered (n)? - the selection of Functional requirements to be removed from the coverage plan
Test SUF% - an rating of the Test coverage Sufficiency that was achieved in verifying a functional requirement
Worksheet Calculation Fields:
Total Impact = the weighted average of all Impact ratings
Total Usage = the weighted average of all Usage ratings
EXECost Scale = the relative scale of the Execution Cost Man Hours to verify this functional requirement
[ 1 = XSmall (<= 2 hrs), 2 = Small (<= 4 hrs), 3 = Medium (<= 8hrs), 4 = Large (<= 12hrs), 5 = XLarge (> 12hrs) ]
Risk Value = the relative weight of functional risk associated to each Functional requirement ( Impact + Usage * PoF )
Priority = the relative priority of its weighted risk ( Risk / Cost )
TTL MH = the Total estimatedin Time in Man Hours for all the Functional requirements
Risk% = the total risk percentage associated with all the functional requirements that will NOT be verified
Coverage% = the total percentage of functional requirements test verification
OPT MH = the total time in Man Hours for the Optimized list of functional requirements to be verified
SUF AVG% = the Average Sufficiency achieved in test coverge achieved across all functional requirements
Execution Steps:
1. Copy this (template) workbook into a new workbook.
a. Name the new workbook, “<RQ#> Approved Risk Based Coverage”
2. From the Test Plan’s Functional Requirements table copy Functional Requirement ID (FRID) into the worksheet, “Risk Based Calculation”. (column B)
a. In the worksheet, insert blank rows as necessary to get enough space to handle all the functional requirements;
b. In the new line copy down the formulas from the row above it (columns K:O)
3. Test Focal requests that all RQ Focals (Dev, PM) complete their portion of the "Risk Based Calculation" worksheet (columns C:K)
a. Each stakeholder (PM, Dev, Test) will rate their separately assigned input fields ( Impact, Usage, PoF, EXECost ) on a relative scale from 1-5 (5 = highest)
4. Test Focal selects those functional requirement to remove from the coverage to meet the scheduling constraints.
a. Sort the "Priority" column in descending order to obtain the top priority requirements at the top of the list (column Q).
b. Select functional requirements to remove from coverage (column R); be cognizant of requirement dependencies in your selection.
c. Test Focal meets with their manager to conduct an internal review of the completed optimized coverage plan.
5. Test Manager executes a review process with Dev (Dev Focal and Dev Manager) to get their approval on the selected requirements and the risk being incurred.
6. Upon approval, Test Focal uploads the approved “<RQ> Approved Risk Based Coverage” workbook as a Test Plan attachment.
a. The "Risk Based Calculation" worksheet from the workbook is copied under the "Risk Based Coverage" section of the Test Plan (Section 2.2.13) in the location indicated in the test plan.
b. In the RQ’s PM Project, update the "Risk Based Coverage" milestones’ "Approved %" field with the approved risk (i.e. “Risk%” field value in the worksheet)
7. After test case execution is completed, the Test Focal downloads the “<RQ#> Approved Risk Based Coverage” workbook and creates a new workbook from it.
a. Name the new workbook, “<RQ#> Final Risk Based Coverage”.
8. In the “<RQ#> Final Risk Based Coverage” workbook, update the “Risk Based Calculation” worksheet with the actual functional requirements coverage achieved.
a. As necessary update which functional requirements were covered in the actual testing (column R).
b. For each tested functional requirement input your test coverage sufficiency evaluation (column S).
c. In the RQ’s PM Project, update the "Risk Based Coverage" milestones’ "Final %" field with the final risk percentage achieved (i.e. “Final%” field value in the worksheet)
d. Copy the “Risk Based Calculation” worksheet under the "Risk Based Coverage" section of the Test Plan (Section 2.2.13) in the location indicated in the test plan.
e. Upload the completed “<RQ#> Final Risk Based Coverage” workbook as a Test Plan attachment.